Shropshire and Wrekin Fire and Rescue Authority

Audit and Performance Management Committee

29 January 2015

Annual Governance Statement 2014/15 Improvement Plan

Report of the Chief Fire Officer

For further information about this report please contact John Redmond, Chief Fire Officer, on 01743 260205 or Ged Edwards, Planning and Performance Manager, on 01743 260208.

Purpose of Report

This report summarises the progress made to date against the improvements contained in the Annual Governance Statement (AGS) Improvement Plan 2014/15.

|  | Recommendations The Committee is asked to note the progress made against each of the improvements contained in the AGS Improvement Plan 2014/15. |
| --- | --- |

Background

The Fire Authority has delegated authority to the Audit and Performance Management Committee to consider and approve the Statement of Accounts for 2013/14.  This was agreed at the September meeting of the Committee.

The Statement of Accounts contains, as an appendix, a statement as to how effective the Authority’s various systems of internal control have been in governing the risks, to which the Authority is exposed.  This is known as the Annual Governance Statement or the AGS.  Areas of the system of internal control that had been identified as requiring improvement were listed in the AGS and an action plan was developed to ensure these improvements are progressed during the coming year (the AGS Improvement Plan 2014/15).

This Committee is responsible for monitoring the progress, which the Service makes against the Plan.

Monitoring Progress against the AGS Improvement Plan 2014/15

A copy of the AGS Improvement Plan 2014/15 is attached as an appendix to this report; progress against each of the planned activities is also included in the appendix.

As is the case with most plans, the activities included within it are often subject to change.  This can be due to changes in the external environment that guides our work, as well as the internal environment that dictates whether we have the capacity to achieve our stated objectives.  To ensure there is control over any slippage, the officers responsible for delivering this work must obtain approval from the Service Management Team or Service Transformation Board, if they require any variations to the current Plan.  These changes will also be reported to this committee.

Progress to date

The 2014/15 Improvement Plan contains 7 areas for improvement.  Progress against each of the work packages is detailed briefly in the appendix.

Financial Implications

There are no financial implications arising from this report.

Legal Comment

There are no legal implications arising from this report.

Initial Impact Assessment

This report contains merely statements of fact / historical data.  An Initial Impact Assessment is not, therefore, required.

Equality Impact Assessment

There are no equality or diversity implications arising from this report.  An Equality Impact Assessment is not, therefore, required.

Appendix

Annual Governance Statement Improvement Plan 2014/15

Background Papers

There are no background papers associated with this report.

| Area of review | IRN | Improvement required | Improvement Owner | Progress to date | Completion date |
| --- | --- | --- | --- | --- | --- |
| Hereford and Worcester (HWFRS) Memorandum of Understanding (MoU) | 1 | Continue with the work with HWFRS on the MOU through the following workpackages: Virtual Private Network (VPN) / Fixed Link Communication Control Interface (CCI) Standardisation of icons on the Integrated Communication Control System (ICCS) Fall back arrangements with Cleveland Fire Brigade Standardisation of mobilising procedures Standardisation of operational procedures | Louise McKenzie | Good progress continues to be made and DCLG visited for the last time in December and reported being extremely impressed with the project results. The installation of the fixed line remains outstanding due to issues that H&W are dealing with. Confirmation of an installation date at their HQ is awaited. Standardisation of mobilising and operational procedures continues and will do so beyond the end of the project plan. Final report to close the Project will be published by DCLG at the end of March 2015. | December 2014 |
| Service Transformation Programme (STP) | 2 | Year three of the Programme Plan was agreed by STP Board at its meeting on 7 May. All the Work Packages and Projects Plans have been identified and resources allocated against them. The main overarching areas of delivery are associated with the development of Resourcelink, SharePoint Implementation, Mobile Working Activities, Improvements to the Command and Control System and Building Improvements. Reports on Programme benefits will be reported to Audit and Performance Management Committee as reviews are undertaken. | Ged Edwards | All Projects/Work Packages are being monitored and progress is reported to the Programme Board. A review of the Programme will be undertaken in March as Year 3 of the programme comes to an end. The Programme is to be re-scoped to include the reviews and implementation projects within Integrated Risk Management Planning (IRMP), and the Programme will now be extended up to 2020 to align with IRMP and the Medium Term Corporate Plan. A number of benefits reviews have commenced and a report will be presented to the Committee in April. | Ongoing. The Programme has now entered year 3 of a 5 year programme |
| Integrated Risk Management Plan (IRMP)/ 20:20 Review | 3 | To ensure the Service is able to deliver the 20:20 process, which involves a series of reviews, consultations and decisions, it is being managed as a project, which will include: Undertaking a thorough review of the Authority’s Strategic IRMP Planning to meet the demands of a much reduced budget, by ensuring the Service’s Public Value process looks further into the future Meeting the requirements of the new Fire and Rescue Service National Framework Document | Andy Johnson | With Phase 3 consultation completed, the Strategic Risk and Planning (StRaP) Group made recommendations to the Strategy and Resources Committee, which were accepted by the Fire Authority at its October meeting. The changes to the document, based on consultation feedback, are being made. The IRMP Action Plan for the coming year will be created and then both documents will be published in April 2015. Approval for these will come to the StRaP Group in January / February 2015 | IRMP Strategic Plan 2015-20 and IRMP Action Plan 2015/16 will be published on Service website on 1st April. Actions will then be implemented and monitored in accordance with those documents. |
| Information and Communications Technology (ICT) Network infrastructure | 4 | Following previous ICT internal audit reports the Service will continue to invest in hardware and communication technologies: That ensure ICT systems are continuously available and failsafe That improve ICT processes and procedures in supporting the day-to-day function of the Department That enable employees to work from any location, on any device and over any connection | Sally Edwards | The main progress has been the migration of the WAN. There were extremely tight deadlines imposed upon us by the incumbent, Shropshire Council, to migrate from the existing WAN by 5 January 2015. An exemption was signed in July 2014 and, while almost unheard of to achieve a migration within 5 months, this was completed successfully with no interruption to business continuity. The new WAN provides greater resilience and has potential for wider benefits, using wireless network technology. | Work is ongoing and will provide continual improvements, monitored through Service Transformation Programme |
| Health and Safety Management | 5 | Implement the action plans following the review of the Health and Safety Executive (HSE) consolidation report, based on the eight inspections completed in 2009/10. | Andy Perry | Continued progress has been made against the outstanding recommendations with changes in some areas of ICT. The Management Information Systems for the recording and auditing of training and assurance are currently being reviewed. This will, in some areas, prolong the recording, monitoring and auditing elements of the HSE Consolidation Report Action Plan. | September 2015 |
| Outcomes of Operational Assurance (OpA) Assessment | 6 | Close-down report, including proposal for the next OPA process, will go to Audit and Performance Management Committee in April 2015. Carry out OpA exercise in 2015 and implement any recommendations. | Rod Hammerton | Some progress had been made in all areas, including those identified as high priority, with notable achievements, such as increased resilience in the control function and a regional approach to adopting operational policy. However, it is evident that there are areas where the expected benefits are yet to be fully realised. A full assessment of performance will be undertaken in February with the objective of producing a close-down report in April and a proposal for a future joint assessment. The overall objective of achieving operational improvements through collaboration with regional partners remains valid but collaboration always increases the complexity of any project and has the potential to reduce the pace of delivery. | April 2015 |
| Payroll Systems Review | 7 | Review and improve payroll systems. | Louise McKenzie/ Joanne Coadey | Good progress is being made in analysing specific payroll elements and there is a considerable volume of work still to do. Officers are streamlining processes and looking to improve efficiency by making some electronic. Officers are also inviting in some professional support to give advice as to what extra skills / resources may be required. | Managed through the Service Transformation Programme |