Shropshire and Wrekin Fire and Rescue Authority

Strategy and Resources Committee

5 February 2015

Capital Update on Activity and Finance

Report of the Chief Fire Officer

For further information about this report please contact John Redmond, Chief Fire Officer, on 01743 260205 or Ged Edwards, Planning and Performance Manager, on 01743 260208.

Purpose of Report

This report provides an overview of all the capital schemes within the Brigade and their current status.

|  | Recommendations The Committee is asked to note the progress so far on current schemes. |
| --- | --- |

Background

Updates on Finance and Activity within Capital Schemes are reported to Members at Strategy and Resources Committee.

This report provides an update on current schemes.

Progress

This report covers the reporting period October to the end of December 2014.  Detailed progress on schemes carried forward from 2013/14 or earlier; and on this year’s schemes (2014/15) is shown within the appendices.

Schemes that are part of the Service Transformation Programme will be monitored by the Service Transformation Board.

Financial Implications

The financial implications are as outlined within the report.

Legal Comment

There are no direct legal implications arising from this report.

Initial Impact Assessment

This report contains merely statements of fact / historical data.  An Initial Impact Assessment is not, therefore, required.

Equality Impact Assessment

Officers have considered the Service’s Brigade Order on Equality Impact Assessments (Personnel 5 Part 2) and have decided that there are no discriminatory practices or differential impacts upon specific groups arising from this report.  An Initial Equality Impact Assessment has not, therefore been completed.

Appendices

Appendix A

Non-exempt Update to end of December 2014 on Schemes carried forward from 2013/14 and prior and on Schemes for 2014/15

Appendix B

Paper 14 Exempt Update to end of December 2014 on Schemes carried forward from 2013/14 and prior and on Schemes for 2014/15

Background Papers

There are no background papers associated with this report.

Schemes carried forward from 2013/14 and prior

| Name of Scheme | Balance Brought Forward from 2013/14 | Spend and commitments to date in 2014/15 | Balance | What is the Scheme End Date? | Senior Responsible Owner and Project Manager or Point of Contact | Update |
| --- | --- | --- | --- | --- | --- | --- |
| Shrewsbury Appliance Bay Doors | £96k | £0k | £96k | December 2014 | Andrew Kelcey | Work on the appliance bay doors has been completed, except for the ceiling works because of structural issues with the columns, which will be addressed through the maintenance budget. Some invoices for the work on the appliance bay doors have been received from Shropshire Council and are currently being processed. |
| Capital Training Improvements 2013/14 and Training Improvements cfwd from 2007/08, 2008/09, 2009/10 and Training Facilities 2010/11 | £159k | £120k | £39k | Unknown | Andy Perry | The work on site at Much Wenlock has now started following a delay in obtaining planning permission. It has also been decided to seek re-approval at Whitchurch, Church Stretton and Clun. Applications have been submitted and are due for determination by 6 February 2015. The design of the underground training facility has been completely revised and further work is now required to develop costs. |
| Light Vehicle Replacement | £82k | £39k | £43k | Unknown | John Das Gupta | Following the review of light vehicles a schedule for potential replacement of light vehicles had been agreed with the Head of Finance and was based upon the vehicle condition rather than just the age. To date two vehicles have been purchased. |
| Replace Ford Rangers and Land Rovers with incident support units (ISUs) with fire fogging capability | £68k | £25k | £43k | March 2015 | Andrew Kelcey | Further expenditure has been incurred on the continued roll out of the fire fogging systems. |
| Fire Alarms on stations | £15k | £6k | £9k | April 2015 | Andrew Kelcey | Single point fire alarm systems have been installed at all sites. Evac chairs have been provided at Shrewsbury and Telford Central. Work to install a fixed alarm at Craven Arms is underway. |

Schemes for 2014/15

| Name of Scheme | Scheme amount | Spend and commitments to date in 2014/15 | Balance | What is the Scheme End Date? | Senior Responsible Owner and Project Manager or Point of Contact | Update |
| --- | --- | --- | --- | --- | --- | --- |
| Thermal Imaging Cameras | £25k | £9k | £16k | March 2015 | Andrew Kelcey | Three cameras were purchased for the new appliances. Further cameras will be purchased as and when required, as opposed to being automatically replaced after a given life cycle. |
| Video conferencing | £69k | £16K | £53K | April 2015 | Sally Edwards | The completion of the Wide Area Network will enable the Service to progress the introduction of Microsoft Lync. |
| IT infrastructure | £100k | £30k | £70k | March 2015 | Sally Edwards | Additional Surface Pro 3s have been purchased in line with the roll out programme. |
| Light pumping unit (to replace the light pumping unit and prime mover schemes and brought forward to 2014/15 as agreed at the April meeting of the Fire Authority) | £500k | £71K | £429K | August 2015 | Andrew Kelcey | The primary contractor and the sub-contractor have now made the necessary weight savings and presented a fully stowed appliance, which is within the weight limit in our specification, resolving the problem previously reported. Chassis delivery to the body builder in Holland is now estimated as April 2015. The appliance will then be shipped to the primary contractor in the UK, where it will be completed. This is estimated at August 15. |
| Improvements at Wellington (Appliance Bay Doors, Dormitories and Heating System) | £270k | £8k | £262k | Dormitories December 2014 Appliance Bay Doors February 2015 Dates still to be confirmed for Heating System | Andrew Kelcey | Stage one, which includes the study rooms, is all complete. Stage two, which includes the new drying room and breathing apparatus servicing area plus moving the pole drop and enclosing the kit room, started on 7 January and good progress has been made. The new appliance bay doors and appliance bay heating will start in early February. |
| Holmatro Pump Replacement | £33k | £47k | £14k over spend | March 2015 | Andrew Kelcey | This scheme is used to replace the Holmatro Pumps as needed each year. The scheme is currently overspent, as officers have taken advantage of competitively priced kit that had become available from the West Midlands Fire Service as a result of reorganisation. |

Please note that there is a second part to this appendix, which is an exempt paper and appears at item 14 on the agenda.